## Summary
<This checklist should be reviewed and customised (if needed), in a first stage, when planning business implementation. It should be based on the information presented in the Business Implementation Plan, but It can also help the Business Manager (BM) and the Project Manager (PM) to define the business implementation activities by identifying key controls. Despite this, the main purpose of the Business Implementation Checklist is to support the Business Manager (BM) and the Project Manager (PM) when verifying whether the business implementation activities were performed as planned.>
Phase-Exit Review
Organisation / Department: | <Name of the organisation / department.>
Project Name: | <Name of the project.>
Project Owner: | <Name of the Project Owner.>
Business Manager: | <Name of the Business Manager.>
Solution Provider: | <Name of the Solution Provider.>
Project Manager: | <Name of the Project Manager.>
Reviewer Name: | <Name of the person performing the phase-exit reviews.>
Overall Compliance (%) | 0%
Overall Phase-Exit Status: | 0
Area | Phase-Exit Status | % of Phase Compliance | Date | Already performed?
Initiating | 0% | 0% | dd/mm/yyyy | No
Planning | 0% | 0% | dd/mm/yyyy | No
Executing | 0% | 0% | dd/mm/yyyy | No
Closing | 0% | 0% | dd/mm/yyyy | No
Assessment Key:
0.3 | Major key activities for the phase(s) weren't performed (50% of the key activities or more are still to be completed).
0.7 | Some key activities are still to be completed before the phase(s) can be closed (% of compliance between 51% and 80%).
0.9 | Nearly all the key activities for the phase(s) are complete (more than 80% of the key activities). The decision to move to another phase should be taken considering the relevance / adequacy of the remaining activities to the project and its specificities.
Yes
No

## Initiating
| Initiating Phase-Exit Checks |  | Date: | dd/mm/yyyy
% of Phase Compliance |  |  | 0% | 0%
# | Description | Answer | Score | Comments
1 | Has a Project Initiation Request been documented and approved? | No | 0 | <Add a justification here>
2 | Are the project context, scope, deliverables and expected outcomes documented? | No | 0
3 | Has a Project Owner (PO) been identified? | No | 0
4 | Are project benefits and success criteria documented? | No | 0 |  | Yes
5 | Are the benefits and success criteria measurable? | No | 0 |  | Yes, Partially
6 | Have all the key project stakeholders been identified? | No | 0 |  | No
7 | Are all the initial roles and responsibilities defined? | No | 0 |  | N/A
8 | Has the Project Steering Committee (PSC) been established? | No | 0
9 | Have at least 4 alternative solutions been analysed e.g. using a SWOT analysis? | No | 0
10 | Are major assumptions, constraints and risks identified? | No | 0
11 | Have project synergies and dependencies been analysed? | No | 0
12 | Has the project Total Cost of Ownership (TCO) been estimated in FTE and €? | No | 0
13 | Are both requestor and solution provider costs included in the project TCO? | No | 0
14 | Are project funding sources (budget lines) identified for each cost element? | No | 0
15 | Have project savings been estimated in FTE and k€? | No | 0
16 | Has a Business Case been documented and approved by the Project Owner (PO)? | No | 0
17 | Is there a Project Manager (PM) assigned to the project? | No | 0
18 | Are requestor needs documented and linked to project deliverables? | No | 0
19 | Is project roadmap (start and end dates) for major milestones and deliverables documented? | No | 0
20 | Is project approach / methodology identified? | No | 0
21 | Are Risk, Issue and Decision Logs setup? | No | 0
22 | Have the identified risks an associated response strategy been approved? | No | 0
23 | Are major resources needed to execute the project identified as well as requirements detailed? | No | 0
24 | Have security, document management and data protection constraints been assessed? | No | 0
25 | Has a Project Charter been documented and approved by the Project Steering Committee (PSC)? | No | 0
26 | Is the project currently delivering to schedule? | No | 0
27 | Is the budget allocated sufficient at this point of the project? | No | 0
28 | Is the project ready to proceed to the Planning Phase? | No | 0
| Total score for compliance | 0 | 0

## Planning
| Planning Phase-Exit Checks |  | Date: | dd/mm/yyyy
% of Phase Compliance |  |  | 0% | 0%
# | Description | Answer | Score | Comments
1 | Is the Stakeholder Matrix complete with all the relevant stakeholders' names and contact details? | No | 0 | <Add a justification here.>
2 | Are all project roles and responsibilities detailed? | No | 0
3 | Is the project scope broken-down in manageable components that allow accurate estimation of resources, work effort and duration? | No | 0 |  | Yes
4 | Is it clear the link between project scope / deliverables and work packages / activities / tasks? | No | 0 |  | Yes, Partially
5 | Are project management and business implementation activities considered in the Project Work Plan? | No | 0 |  | No
6 | Are all the activities / tasks assigned to someone? | No | 0 |  | N/A
7 | Were all the activities / tasks and related effort validated by the task owner / domain expert? | No | 0
8 | Are all project costs / effort estimated and detailed at task level? | No | 0
9 | Are all project work packages, activities and tasks scheduled? | No | 0
10 | Is the critical path identified? | No | 0
11 | Are project performance indicators and metrics defined? | No | 0
12 | Is the Project Work Plan baselined and approved by the Project Steering Committee (PSC)? | No | 0
13 | Are all the communication items (e.g. meetings and reports) defined as well as their frequency? | No | 0
14 | Has a Communications Management Plan been documented, as a separate document or included in the Project Handbook? | No | 0
15 | Is the project management approach detailed and documented in a Project Handbook? | No | 0
16 | Has an escalation process been documented and tailored to risk, issues and change management? | No | 0
17 | Has a Project Change Management Plan been documented, as a separate document or included in the Project Handbook? | No | 0
18 | Are the risk assessment thresholds defined, including the risk appetite? | No | 0
19 | Is a Risk Management Plan documented, as a separate document or included in the Handbook? | No | 0
20 | Is an Issue Management Plan documented, as a separate document or included in the Handbook? | No | 0
21 | Is there a Change Log in place? | No | 0
22 | Were quality requirements, assurance activities and metrics defined and approved by the Project Steering Committee (PSC)? | No | 0
23 | Has a Quality Management Plan been documented, as a separate document or included in the Project Handbook? | No | 0
24 | Are all the deliverables acceptance criteria, activities and metrics defined and approved by the Project Owner (PO)? | No | 0
25 | Has a Deliverables Acceptance Management Plan been documented, as a separate document or included in the Project Handbook? | No | 0
26 | Has a configuration management procedure been documented? | No | 0
27 | Are the project management processes communicated to the Project Core Team (PCT) and to the major project stakeholders? | No | 0
28 | Are all types of resources (people, software, infrastructure, facilities, outsourcers, materials, services,…) identified and their effort and period estimated? | No | 0
29 | Are training needs identified? | No | 0
30 | Has a Resource Plan been documented, as a separate document or included in the Project Handbook? | No | 0
31 | Are all the activities that will be performed by the business/requestor side identified and estimated? | No | 0
32 | Has a Business Implementation Plan been documented? | No | 0
33 | Are the transition activities planned and agreed with the involved stakeholders? | No | 0
34 | Is a Transition Plan documented? | No | 0
35 | Are outsourcing activities and deliverables defined as well as evaluation criteria? | No | 0
36 | Is there an Outsourcing Plan documented, as a separate document or included in the Handbook? | No | 0
37 | Are all project plans approved? | No | 0
38 | Is there a Project Handbook documented? | No | 0
39 | Are all the major deviations from the Project Charter approved by the Project Steering Committee (PSC) / Appropriate Governance Bodies (AGB)? | No | 0
40 | Is the project currently delivering to schedule? | No | 0
41 | Are all resources available for the executing phase? | No | 0
42 | Is the allocated budget sufficient at this point of the project? | No | 0
43 | Is the project ready to proceed to the Executing Phase? | No | 0
| Total score for compliance | 0 | 0

## Executing
| Executing Phase-Exit Checks |  | Date: | dd/mm/yyyy
% of Phase Compliance |  |  | 0% | 0%
# | Description | Answer | Score | Comments
1 | Are resources and budget available to complete activities and to transfer deliverables to the requestor side? | No | 0 | <Add a justification here.> | Yes
2 | Have activities been performed as defined and scheduled in the Project Work Plan? | No | 0 |  | Yes, Partially
3 | Were artefacts produced, updated and revised as planned? | No | 0 |  | No
4 | Were the quality assurance and control activities performed as planned? | No | 0 |  | N/A
5 | Have deliverables been tested / reviewed? | No | 0
6 | Were outsourcing processes and outputs monitored and reviewed? | No | 0
7 | Are tests results, issues and corrective actions documented? | No | 0
8 | Are all major risks mitigated? | No | 0
9 | Were security and data protection issues taken into account? | No | 0
10 | Have all the approved changes been implemented? | No | 0
11 | Are deliverables in line with requestor needs and expectations? | No | 0
12 | Are all the project issues and corrective actions resolved / closed? | No | 0
13 | Are all deliverables (including supporting deliverables such as documentation) ready to be approved by the Project Owner (PO)? | No | 0
14 | Were transition activities performed as planned? | No | 0
15 | Has required training been conducted? | No | 0
16 | Were the relevant stakeholders informed about the delivery of projects outputs? | No | 0
17 | Were project performance indicators and metrics captured and assessed? | No | 0
18 | Were the business implementation activities performed as planned? | No | 0
19 | Have all the communication items (meetings, reports,…) been implemented as planned? | No | 0
20 | Did the Project Owner (PO) formally approve deliverables (final approval)? | No | 0
21 | Are deliverables reviews and approvals documented and performed by the appropriate person (Project Owner, domain expert,…)? | No | 0
22 | Are deliverables fully operational? | No | 0
23 | Is there a formal transfer of responsibilities to the Project Owner (PO) and operations teams? | No | 0
24 | Has a list of planned maintenance / operational actions been provided to the requestor / operations team? | No | 0
25 | Was the transfer of responsibility announced to all stakeholders? | No | 0
26 | Have all deliverables and artefacts been placed in the project repository, e.g. test results, sign-offs, training materials,...? | No | 0
27 | Is project configuration management effective? | No | 0
28 | Are operational/maintenance activities ready to start? | No | 0
29 | Is the project ready to proceed to the Closing Phase? | No | 0
| Total score for compliance | 0 | 0

## Closing
| Closing Phase-Exit Checks |  | Date: | dd/mm/yyyy
% of Phase Compliance |  |  | 0% | 0%
# | Description | Answer | Score | Comments
1 | Did a Project-End Review Meeting take place? | No | 0 | <Add here the justification for the answer given.>
2 | Were final project performance indicators and metrics assessed and compared to project baselines? | No | 0 |  | Yes
3 | Are project benefits and unachieved goals assessed and remaining benefits forecasted? | No | 0 |  | Yes, Partially
4 | Was client / requestor satisfaction assessed? | No | 0 |  | No
5 | In case some risks or issues couldn't be closed, are they re-assessed and follow-up actions recommended? | No | 0 |  | N/A
6 | Are follow-up actions assigned to people and a formal transfer of ownership performed? | No | 0
7 | Were all the hand over activities to the operations mode performed? | No | 0
8 | Are support and maintenance activities running as planned? | No | 0
9 | Did all the relevant stakeholders give feedback on the overall project experience? | No | 0
10 | Were lessons learned and post-project recommendations captured? | No | 0
11 | Is the Project-End Report documented and delivered to the relevant stakeholders? | No | 0
12 | Are project artefacts and other supporting documentation organised and archived in a central repository? | No | 0
13 | Is project archiving following the EC internal policy for records management and archives? | No | 0
14 | Were all the configuration management procedures completed? | No | 0
15 | Were all the security management procedures completed e.g. copies of project data and restriction of project members access to systems and data? | No | 0
16 | Was the project formally accepted by the Project Steering Committee (PSC) / Project Owner (PO)? | No | 0
17 | Have project team members performance been assessed? | No | 0
18 | Is the project team officially released? | No | 0
19 | Have project costs stopped? | No | 0
20 | Is the project ready to be closed? | No | 0
| Total score for compliance | 0 | 0